## SCORES
2022 CALL FOR PROJECTS
PROJECTS
TIP ID | PROJECT TITLE | MUNICIPALITY | PROJECT READINESS | MULTIPLE JURIDISCTION | TRAFFIC VOLUME | SAFETY | PAVEMENT CONDITION | COHORT | GREEN INFRASTRUCTURE | FREIGHT MOVEMENT | COMPLETE STREETS | TOTAL POINTS ALLOWED | NOTES
POSSIBLE POINTS |  |  | 25 | 10 (2.5 per participant) | 15 | 15 | 5 | 5 | 5 | 5 | 15 | 100
CFP12-22-0006 | Theodore Street from Drauden Road to Wesmere Parkway | Joliet | 5 | 0 | 14.2875 | 12 | 0 | 0 | 5 | 2 | 10 | 48.2875 | PR: PHS I ENG SUBMITTED ¦ MJ: 0¦ TV: (9050 x 15/10,000=13.575) + 15 pts = 28.575 /2=14.2875)) ¦ PC: (62,88,83,85,94,56=468/6=78 AVG) ¦ CHRT = 1 ¦ GI: 2+¦ FM: (3.6 + 2.3= 5.9) ¦ CS : C ONLY
CFP12-22-0008 | Seil Road Widening | Shorewood | 15 | 0 | 5.3438 | 0 | 1 | 0 | 2 | 0 | 15 | 38.3438 | PR = PHS II ENG EXC ¦ MJ = 0 ¦ TV = (6650 x 15/10,000 = 9.975 + 475 x15/10,000 = 7.5 =10.6875/2= 5.34375) ¦ SFTY= minimal ¦ PC= (78,78,75,58=289/4=72.25) ¦ CHRT 1 ¦ GI = 1 Element ¦ FM = LOW ¦ CS =P + C
CFP12-22-0009 | Cedar Road at Haven Avenue Roundabout | New Lenox | 15 | 0 | 12.75 | 0 | 3 | 0 | 0 | 0 | 15 | 45.75 | PR = PHS II ENG EXC ¦ MJ = none ¦ TV = (5500x15/10,000= 8.25) +15 +15 =38.25/3=12.75)) ¦ SFTY = minimal ¦ PC = 32,33,21,24,52,34,71,76,67,68=478/10=47.8 avg) ¦ CHRT 1 ¦ GI = 0 Element ¦ FM = LOW ¦ CS = P + C
CFP12-22-0010 | US 45 Shared Use Path - La Porte Road to Birch Avenue | Mokena | 5 | 0 | 2.4 | 0 | 0 | 0 | 2 | 3 | 10 | 22.4 | PR = PDR Submitted March 2022 ¦ MJ = none ¦ TV = (1600 x 15 / 10,000 = 2.4) ¦ SFTY = minimal ¦ PC: No data ¦ CHRT 1 ¦ GI = 1 Element ¦ FM = 6.9% ¦ CS= NO POLICY (Just components)
CFP12-22-0013 | Highpoint Drive Extension from Airport Road to Alder Creek Drive | Romeoville | 5 | 0 | 10.809 | 0 | 0 | 0 | 2 | 0 | 15 | 32.809 | PR: ENG I SUBMITTED ¦ MJ: 0¦ TV: Current ADT (7206x 15/10,000=10.809) ¦ SFTY: minimal¦ PC: No data ¦ CHRT 1 ¦ FM= N/A ¦ CS: P + C
CFP12-22-0014 | Will Road Reconstruction #1 | Diamond | 10 | 10 | 1.95 | 0 | 0 | 5 | 5 | 1 | 15 | 47.95 | PR: PHS 1 DA ¦ MJ: 5 (4 MAX) ¦ TV: (1300X15/10000=1.95) ¦ PC: (89,98=187/2=93.5 AVG)¦ STFY: minimal ¦ CHRT 3 ¦ GI: 3¦ FM: 2-3.99% ¦ CS: P+ C
CFP12-22-0015 | Will Road Reconstruction #2 | Diamond | 10 | 10 | 0.3237 | 0 | 0 | 5 | 5 | 1 | 15 | 46.3237 | PR: PHS 1 DA ¦ MJ: 5 (4 MAX) ¦ TV: (1300X15/10000=1.95) (.35/2.10miles = x/100 = 16.6%, 1300 x 16.6% =215.8 x 15/10,000 =.3237)¦ PC: (94,62,69,89=314/4=78.5)¦ STFY: minimal ¦ CHRT 3 ¦ GI: 3¦ FM: 2-3.99% ¦ CS: P+ C
CFP12-22-0016 | Will Road Reconstruction #3 | Diamond | 10 | 10 | 0.60352 | 0 | 0 | 5 | 5 | 1 | 15 | 46.6035 | PR: PHS I SUBMITTED ¦ MJ: 5 (4 MAX) ¦ TV: (.65/2.10 = x/100 = 30.95%, 1300(30.95%)= 402.35 x 15/10,000=.603525))¦ SFTY=minimal ¦ CHRT=1 ¦ FM= 2-3.99%¦ CS= P + ¦ PC=97.2857,
CFP12-22-0017 | 151st Street | Homer Glen | 10 | 5 | 14.25 | 9 | 0 | 0 | 5 | 1 | 15 | 59.25 | PR: PHS I DA ¦ MJ: 2 ¦ TV: (9500x15/10000=14.25) ¦ SFTY : 9 both medium + high (longer road is medium) ¦ PC: 68,99,100,100,100,100,97,91,72,58=885/10=88.5 ¦ CHRT 1 ¦ GI: 2+ ¦ FM=2% ¦ CS: P + C
CFP12-22-0018 | Normantown Road- Weber Road to 135th Street/South Budler Road | Romeoville | 20 | 0 | 12.4875 | 0 | 5 | 0 | 0 | 4 | 15 | 56.4875 | PR: ROW NN, PHS II EXEC ¦ MJ: 0 ¦ TV= ((7900 x 15/10,000 = 11.85) + (8750 x 15/10,000=13.125) =24.975/2= 12.4875)) ¦ SFTY: minimal ¦PC: 72.15 ¦CHRT 1 ¦ GI: 0 ¦ FM: 9.5% ¦ CS: P + C
CFP12-22-0020 | West Street Reconstruction from Wilmington Road to Corning Avenue | Peotone | 5 | 0 | 2.4 | 0 | 0 | 1 | 5 | 2 | 15 | 30.4 | PR: PHS I ENG SUBMITTED¦ MJ: 0 ¦ TV: (1600x15/10000=2.4) ¦ SFTY: minimal ¦PC: (82,82,86,63=313/4=78.25) ¦ CHRT 2 ¦ FM: 5> x ¦ CS: P+ C
CFP12-22-0021 | Eastern Avenue Reconstruction from North Street to Smith Road | Manhattan | 5 | 0 | 0.712 | 3 | 0 | 1 | 5 | 1 | 15 | 30.712 | PR: PHS I ENG SUMBITTED ¦ MJ: 0¦ TV: (475x15/10000 = 7125/10000= .7125)¦ SFTY: minimal ¦ PC: 47.8 ¦ CHRT 2 ¦GI: ¦ FM: 2% ¦ CS: P+C
CFP12-22-0023 | US Route 30 at Wallin Drive Intersection Improvements | Plainfield | 0 | 0 | 13.4 | 0 | 1 | 0 | 2 | 5 | 15 | 36.4 | PR: PHS I has not begun, ROW not started ¦ MJ: 0 (Requested doesn't identify confirmed funding) ¦ TV: ¦ SFTY = minimal ¦ PC = 67 ¦CHRT 1 ¦ GI=1 ¦ FM= 14.47 ¦ CS: P + C
CFP12-22-0024 | North Broadway Reconstruction Project | Coal City | 10 | 2.5 | 7.8 | 0 | 0 | 3 | 5 | 5 | 15 | 48.3 | PR: DA received since QBS Underway¦ MJ= 1 ¦ TV: ¦ SFTY: NO DATA ¦PC: NO DATA ¦ CHRT 3 ¦ GI: 2 ¦ FM: 20% ¦ CS: P + C
CFP12-22-0025 | Cleveland Avenue Reconstruction | Monee | 5 | 0 | 0 | 0 | 0 | 3 | 0 | 5 | 10 | 23 | PR: ROW NN ¦ MJ: 0 ¦ TV: NO DATA ¦ SFTY: minimal ¦ PC: NO DATA ¦ CHRT 3 ¦ GI: 0¦ FM: 11.7%+¦ CS: C ONLY
CFP12-22-0026 | Brannick Road Reconstruction, Ridge Road to McClindon Road | Minooka | 0 | 0 | 0.9375 | 0 | 1 | 0 | 5 | 0 | 15 | 21.9375 | PR: no ENG started/has not begun/ROW N ¦ MJ: 0 (in discussion/ not confirmed) ¦ SFTY: minimal PC:72 ¦ TV: (625x15/10000=9375/10000=.9375) ¦ CHRT 1 ¦FM: no data ¦ CS: P+C
CFP12-22-0027 | Court Street Sidewalk Extension | Monee | 5 | 0 | 9 | 6 | 1 | 3 | 0 | 2 | 15 | 41 | PR: ROW NN ¦ MJ: 0 ¦ SFTY: low ¦ TV: 9 ¦ PC: 71 ¦ CHRT 3 ¦ GI:0 ¦ FM: 4-5.99% ¦ CS: P +C
CFP12-22-0028 | Laraway Road: US Route 52 to Nelson Road | Joliet/new lenox | 5 | 0 | 10.1625 | 9 | 1 | 0 | 2 | 5 | 15 | 47.1625 | PR: ¦ MJ: 0 ¦ SFTY: 78 Avg ¦ TV: 10.1625 ¦ PC: ¦ CHRT 1 ¦ GI: 1 ¦ FM: 13.2% ¦ SFTY: 8.25 ¦
CFP12-22-0030 | 143rd Street from State Street/Lemont Road to Bell Road | Homer Glen | 5 | 0 | 15 | 12 | 3 | 0 | 0 | 2 | 15 | 52 | TV: >10 ¦ STFY: 12 ¦ GI:0 ¦ MJ: 0 ¦ PR: ENG COMPLETE ¦ FM: 4% ¦ CS: P +C ¦ PC: 48.344
CFP12-22-0031 | Boughton Road Reconstruction; Aspen Drive to just west of Schmidt Road | Bolingbrook | 5 | 0 | 15 | 0 | 3 | 0 | 5 | 2 | 15 | 45 | TV: >10 ¦ CHRT 1 ¦ PC:56.5 ¦ SFTY: minimal ¦ GI: 2+ ¦ CS= P + C ¦ FM: 5.3%
CFP18-22-0017 | IL-171 and New Avenue | Lockport | 5 | 0 | 3.5825 | 0 | 0 | 0 | 5 | 5 | 10 | 28.5825 | PR: ¦ MJ=, TV: ¦ SFTY: minimal (data provided for state st only) ¦ PC: NO DATA ¦ CHRT 1 ¦GI:2 ¦FM: 10.4% ¦ CS: P ONLY
RESURFACING PROJECTS
TIP ID | PROJECT TITLE |  | FINANCIAL COMMITMENT | PAVEMENT CONDITION | TRAFFIC VOLUME | COHORT | GREEN INFRASTRUCTURE | FREIGHT MOBILITY | COMPLETE STREETS | TOTAL POINTS ALLOWED | NOTES
|  | POSSIBLE POINTS | 5 | 35 | 30 | 5 | 5 | 5 | 15 | 100
CFP12-22-0007 | Normantown Road- Crossroads Parkway to Montrose Drive Resurfacing | Romeoville | 2 | 5 | 9.95 | 0 | 0 | 0 | 15 | 31.95
CFP12-22-0011 | 135th Street- Chicago Ship & Sanitary Canal Bridge to New Avenue Resurfacing Project | Romeoville | 2 | 35 | 30 | 0 | 2 | 5 | 15 | 89
CFP12-22-0012 | 191st Street Resurfacing - Wolf Road to US 45 | Mokena | 2 | 5 | 30 | 0 | 0 | 2 | 15 | 54 | PC = 68.16FC= 80%,Cohort 1, GI=, FM=5%,
CFP12-22-0019 | Carbon Hill Road Resurfacing Project | Coal city | 2 | 5 | 9 | 3 | 0 | 2 | 5 | 26 | (LISTED 5% for financial contribution, PC = (70.4%)
CFP12-22-0022 | Court Street LAFO | Monee | 2 | 5 | 9 | 3 | 0 | 2 | 10 | 31 | requesting 80% funding =1 point, traffic ADT was 14300 and 18400, mokena is cohort 1 so 0,
Note on G9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Their project narrative states: 'The existing section of Highpoint Drive to the dead end has average daily traffic (ADT) of 7,206. Once the connection is completed, the projected ADT is 11,200.' I would chat with Hugh about which number to go with, or you could take an average. Reply: I went with the current ADT at the moment.
Note on H13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: looks like the project location has segments that are 'Medium' and 'High' so the average will probably be >9. If this stays as your highest scored project I wouldn't worry too much about how spot on the averaging is. Reply: I can send you a screenshot of the location! It took me a few minutes to locate on the map, I had luck searching for: 'S Creme Rd, Homer Glen, IL, 60491, USA' https://lakecountyil.maps.arcgis.com/apps/webappviewer/index.html?id=9e0e25a18680427085a6c2efdad32bf5 Reply: I TOOK THE AVERAGE Reply: The data shows ‘medium’ and the second half shows is a fraction of the segment there’s no sure way to measure it
Note on E17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I think this should be 0 - they haven't started Phase 1 yet and they also need ROW and it has not yet been cleared Reply: that's why I had it highlighted as such to double check, because some of the applicants select 'other' and place the reasoning and the methodology only grants points based on if they fall in the specific category. He selected other and put 'Concept phase has been completed. This project was originally started as a Local Roads permit project with previous plan submittals made to IDOT.' I emailed him and he said as far as they had gotten he submitted plans to IDOT so that's why I put 5. Reply: happy I'm double checking points some of this is confusing, because it's not super specific.
Note on F17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It looks like they answered no to having additional financial partners, which would make this a 0 - unless they communicated something different to you! Reply: They answered yes. This was the response on the supply document: IDOT: 50% funding request in process. See attached 6-7-2021 letter to IDOT requesting participation in this project and past discussions with IDOT employees detailing the followup required. Reply: It says in progress and when I emailed him he also said they haven’t confirmed it, so Im not sure if I should give them the points or not
Note on E18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It would seem that they received Phase 1 Design Approval (DA) since their Phase 2 QBS process is underway. However, the 'Local Project Development Report for Group II Categorical Exclusions and Design Approval' document they submitted as part of their application materials is not signed. They definitely will get at least 5 points. 10 if they have received DA Reply: Sorry! Plus another 5 points because they need ROW but it's been cleared

## RANKED PROJECTS
RANKED PROJECTS
RANK | TID ID | PROJECT | MUNICIPALITY | SCORE
1 | CFP12-22-0011 | 135th Street- Chicago Ship & Sanitary Canal Bridge to New Avenue Resurfacing Project | Romeoville | 89
2 | CFP12-22-0017 | 151st Street | Homer Glen | 59.25
3 | CFP12-22-0018 | Normantown Road- Weber Road to 135th Street/South Budler Road | Romeoville | 56.49
4 | CFP12-22-0012 | 191st Street Resurfacing - Wolf Road to US 45 | Mokena | 54
5 | CFP12-22-0030 | 143rd Street from State Street/Lemont Road to Bell Road | Homer Glen | 52
6 | CFP12-22-0024 | North Broadway Reconstruction Project | Coal City | 48.3
7 | CFP12-22-0006 | Theodore Street from Drauden Road to Wesmere Parkway | Joliet | 48.29
8 | CFP12-22-0014 | Will Road Reconstruction #1 | Diamond | 47.95
9 | CFP12-22-0028 | Laraway Road: US Route 52 to Nelson Road | Joliet, New Lenox | 47.16
10 | CFP12-22-0016 | Will Road Reconstruction #3 | Diamond | 46.6
11 | CFP12-22-0015 | Will Road Reconstruction #2 | Diamond | 46.32
12 | CFP12-22-0009 | Cedar Road at Haven Avenue Roundabout | New Lenox | 45.75
13 | CFP12-22-0031 | Boughton Road Reconstruction; Aspen Drive to just west of Schmidt Road | Boilingbrook | 45
14 | CFP12-22-0027 | Court Street Sidewalk Extension | Monee | 41
15 | CFP12-22-0008 | Seil Road Widening | Shorewood | 38.34
16 | CFP12-22-0023 | US Route 30 at Wallin Drive Intersection Improvements | Plainfield | 36.4
17 | CFP12-22-0013 | Highpoint Drive Extension from Airport Road to Alder Creek Drive | Romeoville | 32.81
18 | CFP12-22-0007 | Normantown Road- Crossroads Parkway to Montrose Drive Resurfacing | Romeoville | 31.95
19 | CFP12-22-0022 | Court Street LAFO | Monee | 31
20 | CFP12-22-0021 | Eastern Avenue Reconstruction from North Street to Smith Road | Manhattan | 30.71
21 | CFP12-22-0020 | West Street Reconstruction from Wilmington Road to Corning Avenue | Peotone | 30.4
22 | CFP18-22-0017 | IL-171 and New Avenue | Lockport | 28.58
23 | CFP12-22-0019 | Carbon Hill Road Resurfacing Project | Coal City | 26
24 | CFP12-22-0025 | Cleveland Avenue Reconstruction | Monee | 23
25 | CFP12-22-0010 | US 45 Shared Use Path - La Porte Road to Birch Avenue | Mokena | 22.4
26 | CFP12-22-0026 | Brannick Road Reconstruction, Ridge Road to McClindon Road | Minooka | 21.94

## PROGRAM FFY 23-27
RECOMMENDED PROGRAM FFY 23-27
Recommended for funding as requested
Recommended for funding in later year(s)
Recommended for contingency program
GREEN- Recommended for funding as requested BLUE- Recommended for funding in later year(s) WHITE-Recommended for Contingency Program
PROJECT INFORMATION | [5 empty] | RECOMMENDED PROGRAM | [6 empty] | REQUESTED
Points | Rank | CMAP ID | Project | Lead Agency | Municipality | Phases | 2023 | 2024 | 2025 | 2026 | 2027 | 5-Year Total | 5- Year Total
89 | 1 | CFP12-22-0011 | 135th Street- Chicago Ship & Sanitary Canal Bridge to New Avenue Resurfacing Project | Will Co Council | Romeoville | C/CE | 338560 | 0 | 0 | 0 | 0 | 338560 | 338560
59.25 | 2 | CFP12-22-0017 | 151st Street | Will Co Council | Homer Glen | C/CE | 0 | 0 | 0 | 4845000 | 0 | 4845000 | 4845000
56.49 | 3 | CFP12-22-0018 | Normantown Road- Weber Road to 135th Street/South Budler Road | Will Co Council | Romeoville | C/CE | 782000 | 0 | 0 | 0 | 0 | 782000 | 782000
54 | 4 | CFP12-22-0012 | 191st Street Resurfacing - Wolf Road to US 45 | Will Co Council | Mokena | C/CE | 0 | 2392000 | 0 | 0 | 0 | 2392000 | 2392000
52 | 5 | CFP12-22-0030 | 143rd Street from State Street/Lemont Road to Bell Road | Will Co DOT | Homer Glen | C | 0 | 0 | 0 | 3500000 | 3500000 | 7000000 | 7000000
48.3 | 6 | CFP12-22-0024 | North Broadway Reconstruction Project | Will Co Council | Coal City | C/CE | 0 | 0 | 0 | 0 | 5408208 | 5408208 | 5408208
48.29 | 7 | CFP12-22-0006 | Theodore Street from Drauden Road to Wesmere Parkway | Will Co Council | Joliet | C/CE | 0 | 0 | 3116533 | 0 | 0 | 3116533 | 3116533
47.95 | 8 | CFP12-22-0014 | Will Road Reconstruction #1 | Will Co Council | Diamond | C/CE | Request exceeds available funds remaining in any year |  |  |  |  | 0 | 0
47.16 | 9 | CFP12-22-0028 | Laraway Road: US Route 52 to Nelson Road | Will Co DOT | Joliet, New Lenox | C | Request exceeds available funds remaining in any year |  |  |  |  | 0 | 0
46.6 | 10 | CFP12-22-0016 | Will Road Reconstruction #3 | Will Co Council | Diamond | C/CE | Request exceeds available funds remaining in any year |  |  |  |  | 0 | 0
46.32 | 11 | CFP12-22-0015 | Will Road Reconstruction #2 | Will Co Council | Diamond | C/CE | Request exceeds available funds remaining in any year |  |  |  |  | 0 | 0
45.75 | 12 | CFP12-22-0009 | Cedar Road at Haven Avenue Roundabout | Will Co Council | New Lenox | C/CE | 1002000 | 0 | 0 | 0 | 0 | 1002000 | 1002000
45 | 13 | CFP12-22-0031 | Boughton Road Reconstruction; Aspen Drive to just west of Schmidt Road | Will Co Council | Boilingbrook | C | Request exceeds available funds remaining in any year |  |  |  |  | 0 | 0
41 | 14 | CFP12-22-0027 | Court Street Sidewalk Extension | Will Co Council | Monee | ENG II, C/CE | 52000 | 533600 | 0 | 0 | 0 | 585600 | 585600
38.34 | 15 | CFP12-22-0008 | Seil Road Widening | Will Co Council | Shorewood | C/CE | Request exceeds available funds remaining in any year |  |  |  |  | 0 | 0
36.4 | 16 | CFP12-22-0023 | US Route 30 at Wallin Drive Intersection Improvements | Will Co Council | Plainfield | C/CE | Request exceeds available funds remaining in any year |  |  |  |  | 0 | 0
32.81 | 17 | CFP12-22-0013 | Highpoint Drive Extension from Airport Road to Alder Creek Drive | Will Co Council | Romeoville | C/CE | Request exceeds available funds remaining in any year |  |  |  |  | 0 | 0
31.95 | 18 | CFP12-22-0007 | Normantown Road - Crossroads Parkway to Montrose Drive Resurfacing | Will Co Council | Romeoville | C/CE | 616400 | 0 | 0 | 0 | 0 | 616400 | 616400
30.711 | 20 | CFP12-22-0021 | Eastern Avenue Reconstruction from North Street to Smith Road | Will Co Council | Manhattan | C/CE | Request exceeds available funds remaining in any year |  |  |  |  | 0 | 0
30.4 | 21 | CFP12-22-0020 | West Street Reconstruction from Wilmington Road to Corning Avenue | Will Co Council | Peotone | ENG II, C/CE | 200000 | Request exceeds available funds remaining in any year |  |  |  | 200000 | 200000
28.58 | 22 | CFP18-22-0017 | IL-171 and New Avenue | Will Co Council | Lockport | C | Request exceeds available funds remaining in any year |  |  |  |  | 0 | 0
26 | 23 | CFP12-22-0019 | Carbon Hill Road Resurfacing Project | Will Co Council | Coal City | C/CE | 0 | 556400 | 0 | 0 | 0 | 556400 | 556400
23 | 24 | CFP12-22-0025 | Cleveland Avenue Reconstruction | Will Co Council | Monee | ENG II, C/CE | 0 | 0 | 166400 | Request exceeds funds remaining in any year |  | 166400 | 166400
22.4 | 25 | CFP12-22-0010 | US 45 Shared Use Path - La Porte Road to Birch Avenue | Will Co Council | Mokena | ENG II, C/CE | 96000 | 0 | 0 | 446066 | 0 | 542066 | 542066
21.94 | 26 | CFP12-22-0026 | Brannick Road Reconstruction, Ridge Road to McClindon Road | Will Co Council | Minooka | ENG II, C/CE | 0 | 0 | 0 | 230904 | Request exceeds funds | 230904 | 230904
Grand Total | [6 empty] | 3086960 | 3482000 | 3282933 | 9021970 | 8908208 | 27782071 | 27782071
Unprogrammed Balance | [6 empty] | 52345 | 126761 | 129232 | 1607993 | 1906716 | 3823047
RECOMMENDED CONTINGENCY PROJECTS
PROJECT INFORMATION
Points | Rank | CMAP ID | Project |  | Muni/Lead | Phases
47.95 | 8 | CFP12-22-0014 | Will Road Reconstruction #1 |  | Diamond | C/CE
47.16 | 9 | CFP12-22-0028 | Laraway Road: US Route 52 to Nelson Road |  | Joliet, New Lenox | C
46.6 | 10 | CFP12-22-0016 | Will Road Reconstruction #3 |  | Diamond | C/CE
46.32 | 11 | CFP12-22-0015 | Will Road Reconstruction #2 |  | Diamond | C/CE
45 | 13 | CFP12-22-0031 | Boughton Road Reconstruction; Aspen Drive to just west of Schmidt Road |  | Boilingbrook | C
38.34 | 15 | CFP12-22-0008 | Seil Road Widening |  | Shorewood | C/CE
36.4 | 16 | CFP12-22-0023 | US Route 30 at Wallin Drive Intersection Improvements |  | Plainfield | C/CE
32.81 | 17 | CFP12-22-0013 | Highpoint Drive Extension from Airport Road to Alder Creek Drive |  | Romeoville | C/CE
30.711 | 20 | CFP12-22-0021 | Eastern Avenue Reconstruction from North Street to Smith Road |  | Manhattan | C/CE
30.4 | 21 | CFP12-22-0020 | West Street Reconstruction from Wilmington Road to Corning Avenue |  | Peotone | C/CE
28.58 | 22 | CFP18-22-0017 | IL-171 and New Avenue |  | Lockport | C
23 | 24 | CFP12-22-0025 | Cleveland Avenue Reconstruction |  | Monee | C/CE
21.94 | 26 | CFP12-22-0026 | Brannick Road Reconstruction, Ridge Road to McClindon Road |  | Shorewood | C/CE

## REQUEST - RECOMMENDED FFY23-27
RECOMMENDED PROGRAM | [12 empty] | REQUESTED PROGRAM
PROJECT INFORMATION | [5 empty] | RECOMMENDED PROGRAM | [6 empty] | REQUESTED
Points | Rank | CMAP ID | Project | Lead Agency | Municipality | Phases | 2023 | 2024 | 2025 | 2026 | 2027 | 5-Year Total | Phase | 2023 | 2024 | 2025 | 2026 | 2027 | 5- Year Total
89 | 1 | CFP12-22-0011 | 135th Street- Chicago Ship & Sanitary Canal Bridge to New Avenue Resurfacing Project | Will Co Council | Romeoville | C/CE | 338560 | 0 | 0 | 0 | 0 | 338560 | C/CE | 338560 | 0 | 0 | 0 | 0 | 338560
59.25 | 2 | CFP12-22-0017 | 151st Street | Will Co Council | Homer Glen | C/CE | 0 | 0 | 0 | 4845000 | 0 | 4845000 | C/CE | 0 | 0 | 4845000 | 0 | 0 | 4845000
56.49 | 3 | CFP12-22-0018 | Normantown Road- Weber Road to 135th Street/South Budler Road | Will Co Council | Romeoville | C/CE | 782000 | 0 | 0 | 0 | 0 | 782000 | C/CE | 782000 | 0 | 0 | 0 | 0 | 782000
54 | 4 | CFP12-22-0012 | 191st Street Resurfacing - Wolf Road to US 45 | Will Co Council | Mokena | C/CE | 0 | 2392000 | 0 | 0 | 0 | 2392000 | C/CE | 2392000 | 0 | 0 | 0 | 0 | 2392000
52 | 5 | CFP12-22-0030 | 143rd Street from State Street/Lemont Road to Bell Road | Will Co DOT | Homer Glen | C | 0 | 0 | 0 | 3500000 | 3500000 | 7000000 | C | 0 | 3500000 | 3500000 | 0 | 0 | 7000000
48.3 | 6 | CFP12-22-0024 | North Broadway Reconstruction Project | Will Co Council | Coal City | C/CE | 0 | 0 | 0 | 0 | 5408208 | 5408208 | C/CE | 0 | 0 | 0 | 5408208 | 0 | 5408208
48.29 | 7 | CFP12-22-0006 | Theodore Street from Drauden Road to Wesmere Parkway | Will Co Council | Joliet | C/CE | 0 | 0 | 3116533 | 0 | 0 | 3116533 | C/CE | 0 | 0 | 3116533 | 0 | 0 | 3116533
47.95 | 8 | CFP12-22-0014 | Will Road Reconstruction #1 | Will Co Council | Diamond | C/CE | 0 | 0 | 0 | 0 | 0 | 0 | C/CE | 6847329 | 0 | 0 | 0 | 0 | 6847329
47.16 | 9 | CFP12-22-0028 | Laraway Road: US Route 52 to Nelson Road | Will Co DOT | Joliet, New Lenox | C | 0 | 0 | 0 | 0 | 0 | 0 | C | 5062074 | 0 | 0 | 0 | 0 | 5062074
46.6 | 10 | CFP12-22-0016 | Will Road Reconstruction #3 | Will Co Council | Diamond | C/CE | 0 | 0 | 0 | 0 | 0 | 0 | C/CE | 4023829 | 0 | 0 | 0 | 0 | 4023829
46.32 | 11 | CFP12-22-0015 | Will Road Reconstruction #2 | Will Co Council | Diamond | C/CE | 0 | 0 | 0 | 0 | 0 | 0 | C/CE | 2902903 | 0 | 0 | 0 | 0 | 2902903
45.75 | 12 | CFP12-22-0009 | Cedar Road at Haven Avenue Roundabout | Will Co Council | New Lenox | C/CE | 1002000 | 0 | 0 | 0 | 0 | 1002000 | C/CE | 1002000 | 0 | 0 | 0 | 0 | 1002000
45 | 13 | CFP12-22-0031 | Boughton Road Reconstruction; Aspen Drive to just west of Schmidt Road | Will Co Council | Boilingbrook | C | 0 | 0 | 0 | 0 | 0 | 0 | C | 5062074 | 0 | 0 | 0 | 0 | 5062074
41 | 14 | CFP12-22-0027 | Court Street Sidewalk Extension | Will Co Council | Monee | ENG II, C/CE | 52000 | 533600 | 0 | 0 | 0 | 585600 | ENG II, C/CE | 52000 | 533600 | 0 | 0 | 0 | 585600
38.34 | 15 | CFP12-22-0008 | Seil Road Widening | Will Co Council | Shorewood | C/CE | 0 | 0 | 0 | 0 | 0 | 0 | C/CE | 0 | 4600000 | 0 | 0 | 0 | 4600000
36.4 | 16 | CFP12-22-0023 | US Route 30 at Wallin Drive Intersection Improvements | Will Co Council | Plainfield | C/CE | 0 | 0 | 0 | 0 | 0 | 0 | C/CE | 0 | 0 | 0 | 4845000 | 0 | 4845000
32.81 | 17 | CFP12-22-0013 | Highpoint Drive Extension from Airport Road to Alder Creek Drive | Will Co Council | Romeoville | C/CE | 0 | 0 | 0 | 0 | 0 | 0 | C/CE | 4545904 | 0 | 0 | 0 | 0 | 4545904
31.95 | 18 | CFP12-22-0007 | Normantown Road - Crossroads Parkway to Montrose Drive Resurfacing | Will Co Council | Romeoville | C/CE | 616400 | 0 | 0 | 0 | 0 | 616400 | C/CE | 616400 | 0 | 0 | 0 | 0 | 616400
30.711 | 20 | CFP12-22-0021 | Eastern Avenue Reconstruction from North Street to Smith Road | Will Co Council | Manhattan | C/CE | 0 | 0 | 0 | 0 | 0 | 0 | C/CE | 0 | 0 | 3224000 | 0 | 0 | 3224000
30.4 | 21 | CFP12-22-0020 | West Street Reconstruction from Wilmington Road to Corning Avenue | Will Co Council | Peotone | ENG II | 200000 | 0 | 0 | 0 | 0 | 200000 | ENG II, C/CE | 200000 | 0 | 2240000 | 0 | 0 | 2440000
28.58 | 22 | CFP18-22-0017 | IL-171 and New Avenue | Will Co Council | Lockport | C | 0 | 0 | 0 | 0 | 0 | 0 | C | 0 | 0 | 4845000 | 0 | 0 | 4845000
26 | 23 | CFP12-22-0019 | Carbon Hill Road Resurfacing Project | Will Co Council | Coal City | C/CE | 0 | 556400 | 0 | 0 | 0 | 556400 | C/CE | 0 | 556400 | 0 | 0 | 0 | 556400
23 | 24 | CFP12-22-0025 | Cleveland Avenue Reconstruction | Will Co Council | Monee | ENG II | 0 | 0 | 166400 | 0 | 0 | 166400 | ENG II, C/CE | 0 | 166400 | 2392000 | 0 | 0 | 2558400
22.4 | 25 | CFP12-22-0010 | US 45 Shared Use Path - La Porte Road to Birch Avenue | Will Co Council | Mokena | ENG II, C/CE | 96000 | 0 | 0 | 446066 | 0 | 542066 | ENG II, C/CE | 96000 | 446066 | 0 | 0 | 0 | 542066
21.94 | 26 | CFP12-22-0026 | Brannick Road Reconstruction, Ridge Road to McClindon Road | Will Co Council | Minooka | ENG II | 0 | 0 | 0 | 230904 | 0 | 230904 | ENG II, C/CE | 0 | 230904 | 3562486 | 0 | 0 | 3793390
Grand Total | [6 empty] | 3086960 | 3482000 | 3482000 | 9021970 | 8908208 | 27443511 | Total | 33584513 | 10033370 | 27725019 | 10253208 | 0 | 81596110
Unprogrammed Balance | [6 empty] | 52345 | 126761 | 126761 | 1607993 | 1906716 | 3820576
Recommended for funding as requested
Recommended for funding in later year(s)
Recommended for contingency program
COST INCREASE
31 | 19 | CFP12-22-0022 | Court Street LAFO | Monee | c/ce | cost increase FFY22 |  | Resurfacing Project |  | 404800
RECOMMENDED CONTINGENCY PROJECTS
PROJECT INFORMATION
Points | Rank | CMAP ID | Project |  | Muni/Lead | Phases
47.95 | 8 | CFP12-22-0014 | Will Road Reconstruction #1 |  | Diamond | C/CE
47.16 | 9 | CFP12-22-0028 | Laraway Road: US Route 52 to Nelson Road |  | Joliet, New Lenox | C
46.6 | 10 | CFP12-22-0016 | Will Road Reconstruction #3 |  | Diamond | C/CE
46.32 | 11 | CFP12-22-0015 | Will Road Reconstruction #2 |  | Diamond | C/CE
45 | 13 | CFP12-22-0031 | Boughton Road Reconstruction; Aspen Drive to just west of Schmidt Road |  | Boilingbrook | C
38.34 | 15 | CFP12-22-0008 | Seil Road Widening |  | Shorewood | C/CE
36.4 | 16 | CFP12-22-0023 | US Route 30 at Wallin Drive Intersection Improvements |  | Plainfield | C/CE
32.81 | 17 | CFP12-22-0013 | Highpoint Drive Extension from Airport Road to Alder Creek Drive |  | Romeoville | C/CE
30.711 | 20 | CFP12-22-0021 | Eastern Avenue Reconstruction from North Street to Smith Road |  | Manhattan | C/CE
30.4 | 21 | CFP12-22-0020 | West Street Reconstruction from Wilmington Road to Corning Avenue |  | Peotone | C/CE
28.58 | 22 | CFP18-22-0017 | IL-171 and New Avenue |  | Lockport | C
23 | 24 | CFP12-22-0025 | Cleveland Avenue Reconstruction |  | Monee | C/CE
21.94 | 26 | CFP12-22-0026 | Brannick Road Reconstruction, Ridge Road to McClindon Road |  | Shorewood | C/CE