## Update form
STP-Shared Fund Quarterly Status Update (projects processed through IDOT/FHWA)
Project: |  |  |  |  | TIP ID:
UPDATE INFORMATION |  |  |  |  | PROJECT INFORMATION
| Completed By: | Date:
Initial Submittal |  | <m/d/yyyy> |  |  | Environmental Class of Action: |  | <class of action> |  | <status> |  | <approval date>
Most Recent Prior Update |  | <m/d/yyyy> |  |  | Target Construction Letting: |  | <date>
Current Update |  | <m/d/yyyy> |  |  | Current construction cost estimate: |  | <whole dollars>
Final "Actual" Dates |  | <m/d/yyyy> |  |  | Change in estimate since prior update: |  | <whole dollars> | <describe primary reason(s) for change>
[5 empty] | Most recent PPI approval: |  | <date>
[5 empty] | Most recent GATA periodic report (BoBS 2832): |  | <date>
MILESTONE INFORMATION
No changes from prior update
| Milestone (Shaded lines required for federally-funded phases only) | Initial Estimated Date (m/yyyy) | Complete? | Updated Estimated Date (m/yyyy) | Actual Date (m/d/yyyy) | Attachments (R - Required, O - Optional) | Sponsor/Implementer Comments |  |  | Notes/Instructions
Pre-phase 1 | Project Scoping |  | <yes/no>
| Application for ENG1 Funds |  | <yes/no or n/a>
| Phase 1 QBS Advertisement |  | <yes/no or n/a>
| Phase 1 QBS Closed |  | <yes/no or n/a>
| Consultant Selected by Local Council/Board |  | <yes/no or n/a> |  |  | Meeting minutes (O)
Phase 1 ENG | Engineering Agreement submitted (BLR 5611) |  | <yes/no or n/a>
Federally-funded | LAA submitted (BLR 5310) |  | <yes/no or n/a>
| Engineering Agreement Approved (BLR 5611) |  | <yes/no or n/a> |  |  | Notice to proceed (O) |  |  |  | expected 8-12 months after draft submittal
| LAA approved (BLR 5310) |  | <yes/no or n/a> |  |  | Approved agreement (R) |  |  |  | expected 8-12 months after draft submittal
| Phase 1 Kick-off Held |  | <yes/no> |  |  | Meeting minutes (R)
| Initial PPI Submittal |  | <yes/no or n/a>
| Initial PPI Approval |  | <yes/no or n/a> |  |  | PPI Form (R) |  |  |  | expected 5-10 days after draft submittal
| 1st State/Fed Coord Meeting |  | <yes/no or n/a> |  |  | Meeting minutes (R)
| Environmental Action Concurrence |  | <yes/no or n/a> |  |  | Copy of email/letter/form (R)
| Environmental Survey Request (ESR) submitted |  | <yes/no or n/a> |  |  | Copy of request (O) |  |  |  | See BLRS manual for environmental requirements
| Cultural |  | <yes/no or n/a>
| Section 4(f) approval |  | <yes/no or n/a> |  |  | Copy of approval form/letter (O) |  |  |  | If "n/a" selected, attach form BLR 22410
| Section 6(f) approval |  | <yes/no or n/a> |  |  | Copy of approval form/letter (O)
| Historic Preservation Compliance |  | <yes/no or n/a> |  |  | Copy of approval form/letter (O)
| Noise |  | <yes/no or n/a>
| Floodplain |  | <yes/no or n/a>
| Wetland |  | <yes/no or n/a>
| Wetland Impact Evaluation (WIE) |  | <yes/no or n/a>
| Bio - USFWS Coordination |  | <yes/no or n/a>
| EcoCAT submitted |  | <yes/no or n/a>
| Special Waste |  | <yes/no or n/a>
| PESA Requested |  | <yes/no or n/a> |  |  | Copy of request
| PESA Completed |  | <yes/no or n/a>
| PSI Requested |  | <yes/no or n/a> |  |  | Copy of request
| PSI Completed |  | <yes/no or n/a>
| Public Meeting |  | <yes/no or n/a>
| Subsequent State/Fed Coord Meeting |  | <yes/no or n/a>
| Subsequent State/Fed Coord Meeting |  | <yes/no or n/a>
| Subsequent State/Fed Coord Meeting |  | <yes/no or n/a>
| Project Dev. Report (BLR 19100 or 22210) Submitted |  | <yes/no or n/a> |  |  | Copy of transmittal/cover only (R)
| Project Dev. Report (BLR 19100 or 22210) Approved |  | <yes/no or n/a> |  |  | Signature page (R)
| Phase 1 Design Approval Received |  | <yes/no> |  |  | Signature page (R)
| Initial Invoice (BLR 5620, 5621, 5621-A, -B, -C) |  | <yes/no or n/a>
| Final Invoice/Final Report (BLR 5613 or 13510) |  | <yes/no or n/a>
Phase 2 ENG | Application for ENG2 Funds |  | <yes/no or n/a>
Federally-funded | Phase 2 QBS Advertisement |  | <yes/no or n/a>
| Phase 2 QBS Closed |  | <yes/no or n/a>
| Consultant Selected by Council/Board |  | <yes/no or n/a> |  |  | Meeting minutes (O)
| Updated PPI Submittal |  | <yes/no or n/a>
| Updated PPI Approval |  | <yes/no or n/a> | [6 empty] | expected 5-10 days after draft submittal
| Engineering Agreement submitted (BLR 5611) |  | <yes/no or n/a>
| LAA submitted (BLR 5310) |  | <yes/no or n/a>
| Engineering Agreement Approved (BLR 5611) |  | <yes/no or n/a> |  |  | Notice to proceed (O) |  |  |  | expected 8-12 months after draft submittal
| LAA approved (BLR 5310) |  | <yes/no or n/a> |  |  | Approved agreement (R) |  |  |  | expected 8-12 months after draft submittal
| Phase 2 Kick-off Held |  | <yes/no> |  |  | Meeting minutes (R)
| State/Fed Coord Meeting |  | <yes/no or n/a> |  |  | Meeting minutes (R)
| Pre-final plans submitted |  | <yes/no> |  |  | Copy of transmittal only (R) |  |  |  | Do not attach a full set of plans
| Comments received |  | <yes/no> | [6 empty] | expected 1-4 months after draft submittal
| Final Plans, Specs, and Estimates submitted |  | <yes/no> |  |  | Copy of transmittal (R) |  |  |  | Do not attach a full set of plans
| Initial Invoice (BLR 5620, 5621, 5621-A, -B, -C) |  | <yes/no or n/a>
| Final Invoice/Final Report (BLR 5613 or 13510) |  | <yes/no or n/a>
ROW | Application for ROW funds |  | <yes/no or n/a>
None required | Updated PPI Submittal |  | <yes/no or n/a>
Federally-funded | Updated PPI Approval |  | <yes/no or n/a> |  |  | Approved PPI (R) |  |  |  | expected 5-10 days after draft submittal
| LAA submitted (BLR 5310) |  | <yes/no or n/a> | [6 empty] | expected 4-6 months after draft submittal
| LAA approved (BLR 5310) |  | <yes/no or n/a> |  |  | Approved Agreement (R) |  |  |  | expected 4-6 months after draft submittal
| Initiated |  | <yes/no or n/a>
| Completed |  | <yes/no or n/a>
| Certified |  | <yes/no or n/a>
| Initial Invoice (BLR 5620, 5621, 5621-A, -B, -C) |  | <yes/no or n/a>
| Final Invoice/Final Report (BLR 5613 or 13510) |  | <yes/no or n/a>
Construction/CE | Application for CON/CE funds |  | <yes/no or n/a>
CON federally-funded | Updated PPI Submittal |  | <yes/no>
CE federally-funded | Updated PPI Approval |  | <yes/no> |  |  | Approved PPI (R) |  |  |  | expected 5-10 days after draft submittal
| Draft Construction Agreement submitted (BLR 5310) |  | <yes/no or n/a>
| Draft Construction Eng Agreement submitted (BLR 5610) |  | <yes/no or n/a>
| Final Construction Agreement submitted (BLR 5310) |  | <yes/no or n/a> | [6 empty] | expected 4-6 months after draft submittal
| Final Construction Eng Agreement submitted (BLR 5610) |  | <yes/no or n/a> | [6 empty] | expected 4-6 months after draft submittal
| Final Construction Agreement approved (BLR 5310) |  | <yes/no or n/a> |  |  | Approved Agreement (R) |  |  |  | expected 3-4 months after draft submittal
| Final Construction Eng Agreement approved (BLR 5610) |  | <yes/no or n/a> |  |  | Approved Agreement (R) |  |  |  | expected 3-4 months after draft submittal
| Letting |  | <yes/no>
| Bid Acceptance |  | <yes/no>
| Notice to Proceed |  | <yes/no or n/a>
| Initial Invoice (BLR 5620, 5621, 5621-A, -B, -C) |  | <yes/no or n/a>
| Final Invoice/Final Report (BLR 5613 or 13510) |  | <yes/no or n/a>
Other project activities | Project groundbreaking ceremony |  | <yes/no or n/a>
| Project ribbon cutting ceremony |  | <yes/no or n/a>
| <enter activity> |  | <yes/no or n/a>
| <enter activity> |  | <yes/no or n/a>
| <enter activity> |  | <yes/no or n/a>
| <enter activity> |  | <yes/no or n/a>

## drop-down values
Dropdown: CA (cell H4) | Dropdown: CAStat (cell H4) | Dropdown: LetType (cell H5) | General
<class of action> | <status> | <type> | <yes/no or n/a> | <yes/no>
CE, Group 1, No report (State Approval) | Anticipated | State | Yes | Yes
CE, Group 1, with report (State Approval) | Approved | Local | No | No
CE, Group 2 (Federal Approval) |  |  | N/A
Environmental Assessment (EA)
Env. Impact Statement (EIS)